| PDSA CYCLE # |  | Practice Name: |  |
| --- | --- | --- | --- |

Change Option B: Providing Patient Education Materials Before and During Visits

OVERALL AIM:

By June 30, 2018, increase delivery of HPV vaccine by 10 percentage points above baseline for patients ages 11-17 seen for any office visit.

CHANGE IDEA: Add patient education materials about adolescent vaccines/HPV vaccine before/during visits.

MEASURES (Run charts will be provided by VHealth):

1.       Primary Outcome: Receipt of next dose due during well visits (% of visits)

2.       Process Measure: Well visits with documented provider recommendation (% of visits)

INSTRUCTIONS: This PDSA form contains sample text as a guide. Please modify the Plan table as needed for your practice. Next, refer to the examples in the Do, Study, and Act sections. Then fill in these sections for your practice as you carry out the PDSA cycle.

PLAN: Outline tasks and assignments for this test of change. Revise for each new PDSA cycle.

Start on a small scale or with a few steps of the entire process, then expand the scale and scope in subsequent cycles.

| Tasks | Person(s) Responsible | Where to be done | Start date (update each cycle) | Resources |
| --- | --- | --- | --- | --- |
| Providers and practice staff discuss and agree on how to integrate materials into workflow. Team will start with 11-12 year old well visits then add 13+ well visits in subsequent PDSA cycles. | Operations Champion | Staff meeting | Jan 8 | Sample workflow Documenting HPV Vaccine Refusals in EHR (download) |
| When patients check in for well visit, Admin staff give patient education flyer. | Operations Champion | Front Desk | Jan 10-11 (13+ TBA) | 11-12: Bug Your Doc flyer 13+: HPV flyer |
| After intake, Nurse/MA ask parent to watch video & browse get3shots.org website on phone in exam room | Nurse Manager | Exam room | Jan 10-11 | Bug Your Doc website (http://www.get3shots.org/) |
| Front desk staff and Nurse/MA agree to note any questions or responses and Talking Points to provide appropriate responses. | Operations Champion | Log kept at Front Desk | Jan 10-11 | Talking Points for Staff Spiral notebook |
| Providers use FAQ handout when needed for parents who hesitate to accept recommendation or have in-depth questions | Physician Champion | Exam room | Jan 10-11 | Frequently Asked Questions (FAQ) handout |

DO: Make note of what you did and how it went. Note any problems or surprises.

Example: - The team started with 11-12 year well visits and implemented the plan for two days. - There were 8 patients who were due for adolescent vaccines during the 2-day test. - Two parents asked questions about the HPV vaccine at the Front Desk; the Admin Staff used Talking Points to respond. - One patient/parent did not have a smart phone. This patient refused the HPV vaccine. She said she wanted to “think about it.”

- [Write in your practice’s observations here]

STUDY: Review the data and discuss observations, challenges, unexpected results, and lessons learned.

Example: - The Operations Champion used the VHealth dashboard to look at the well patient visits for Jan 10-11 (the 2-day test). - Process measure: All providers documented recommending all 3 vaccines (given or refused) to the 8 patients who were due (100%) - Primary outcome: 7 of the 8 patients received the next HPV dose due (88%). Comparing to the baseline run chart, the percentage was 64% for all providers combined during the same week in 2017. We saw a big change, even though we were only testing the change for two days. - The provider documented the one refusal and noted “delay for future visit” in the clinical notes.

- [Write in your practice’s results and lessons learned here]

- Process measure:

- Primary outcome:

ACT: Plan for next cycle or adopt the final plan

If this test did not work out well: ABANDON - Modify the plan based on what you learned to test a NEW strategy on a small scale in the next PDSA cycle.

If this test was successful: ADAPT - For the next PDSA cycle, either increase the SCALE (e.g., add more providers, patients, or days) or increase the SCOPE (e.g., add more tasks or steps to the workflow).

After several cycles: ADOPT - Once you have fully implemented a change that is working well and your team is satisfied with the impact, adopt it as standard practice.

Example: - The team decided to adapt the plan by “scaling up” the second PDSA cycle and testing the change for 10 days. - Future PDSA cycles will expand scope to add well visits for ages 13+ and to add sending emails to parents prior to visits.

- [Write in what you will test in the next cycle]