| PDSA CYCLE # |  | Practice Name: |  |
| --- | --- | --- | --- |

Change Option C: Using Prompts to Remind Providers to Offer All Vaccines Due in a Visit

OVERALL AIM:

By June 30, 2018, increase delivery of HPV vaccine by 10 percentage points above baseline for patients ages 11-17 seen for any office visit.

CHANGE IDEA: Use prompts to remind providers to offer all vaccines due in a visit.

MEASURES (Run charts will be provided by VHealth):

1.       Primary Outcome: Receipt of next dose due during WELL visits (% of visits)

2.       Process Measure: Well visits with documented provider recommendation (% of visits)

INSTRUCTIONS: This PDSA form contains sample text as a guide. Please modify the Plan table as needed for your practice. Next, refer to the examples in the Do, Study, and Act sections. Then fill in these sections for your practice as you carry out the PDSA cycle.

PLAN: Outline tasks and assignments for this test of change. Revise for each new PDSA cycle.

Start on a small scale or with a few steps of the entire process, then expand the scale and scope in subsequent cycles.

| Tasks | Person(s) Responsible | Where to be done | Start date (update each cycle) | Resources |
| --- | --- | --- | --- | --- |
| Providers agree on how they would like a new alert to appear on the face sheet of the patient record in the EHR; Submit request for technical assistance from VHealth | Physician Champion | Provider meeting | Jan 8 | Sample workflow Documenting HPV Vaccine Refusals in EHR (download) |
| VHealth customizes EHR to prompt providers at time of visit for vaccines due; provides EHR-specific screenshots of new prompt | Operations Champion | EHR/office | Jan 15 |  |
| Operations Champion and reviews the new prompt with Physician Champion and Dr. C and how it will fit in workflow | Operations Champion | EHR/office | Jan 15 |  |
| Physician Champion and Dr. C start to test the new prompt | Practice Champion | Exam room | Jan 16 |  |

DO: Make note of what you did and how it went. Note any problems or surprises.

Example: - The PC and Dr. C implemented the plan for one day. - The PC and Dr. C each had 4 patients who were eligible for the HPV vaccine on the test day (8 total). - Both providers felt that the prompt was a helpful tool, but they felt the location of the alert was not very noticeable.

- [Write in your practice’s observations here]

STUDY: Review the data and discuss observations, challenges, unexpected results, and lessons learned.

Example: - The Operations Champion used the VHealth dashboard to look at the well visit coverage for the 1-day test period. - Process measure: Both the PC and Dr. C documented recommending the HPV vaccine (given or refused) to all 8 patients who were due. - Primary outcome: 7 of the 8 patients agreed to get the next HPV dose due (88%). Comparing to the baseline run chart, the percentage was 66% for all providers combined during the same week in 2017. We were surprised (and happy) to see such a big change, because it was a short test. - For the patient who refused, the reason documented was documented in the clinical notes as parental refusal (delay for future visit).

- [Write in your practice’s results and lessons learned here]

- Process measure:

- Primary outcome:

ACT: Plan for next cycle or adopt the final plan

If this test did not work out well: ABANDON - Modify the plan based on what you learned to test a NEW strategy on a small scale in the next PDSA cycle.

If this test was successful: ADAPT - For the next PDSA cycle, either increase the SCALE (e.g., add more providers, patients, or days) or increase the SCOPE (e.g., add more tasks or steps to the workflow).

After several cycles: ADOPT - Once you have fully implemented a change that is working well and your team is satisfied with the impact, adopt it as standard practice.

Example: - The team decided to adapt the plan by asking VHealth to move the alert to a new location, then test it again for one day. - Future PDSA cycles will “scale up” by testing the change with all five providers for 2 days. They will also expand scope by adding a step to review the prompt screenshots and instructions with all providers.

- [Write in what you will test in the next cycle]