| PDSA CYCLE # |  | Practice Name: |  |
| --- | --- | --- | --- |

Change Option D: Reminding Parents to Complete Follow-Up Doses of HPV Vaccine

OVERALL AIM:

By June 30, 2018, increase delivery of HPV vaccine by 10 percentage points above baseline for patients ages 11-17 seen for any office visit.

CHANGE IDEA: Make appointments for 2nd/3rd doses at time of 1st dose visit; use reminder system for follow up appointments.

MEASURES (Run charts will be provided by VHealth):

1.       Primary Outcome: Receipt of next dose due during well visits (% of visits)

2.       Process Measure: Well visits with documented provider recommendation (% of visits)

INSTRUCTIONS: This PDSA form contains sample text as a guide. Please modify the Plan table as needed for your practice. Next, refer to the examples in the Do, Study, and Act sections. Then fill in these sections for your practice as you carry out the PDSA cycle.

PLAN: Outline tasks and assignments for this test of change. Revise for each new PDSA cycle.

Start on a small scale or with a few steps of the entire process, then expand the scale and scope in subsequent cycles.

| Tasks | Person(s) Responsible | Where to be done | Start date (update each cycle) | Resources |
| --- | --- | --- | --- | --- |
| Operations Champion requests technical assistance from VHealth to set up automated appointment reminders for 2nd/3rd doses. | Operations Champion | Office | Jan 8 | VHealth |
| VHealth assists with system set up. | Operations Champion | Appointment system | Jan 15 | VHealth |
| Providers and staff agree on how to integrate HPV Vaccine Return Visits form into workflow to ensure that appointments get scheduled for follow up doses before patient leaves. | Physician Champion | Staff Meeting | Jan 18 | Sample workflow |
| Return Visits form stored in exam room. After giving HPV dose, Nurse/MA writes down date on form for 2-dose or 3-dose schedule, then parent schedules appointment(s) at check out. | Nurse Manager | Exam room | Jan 22 | HPV Vaccine Return Visits form |
| Nurses/MAs and check out staff test using Return Visits form for 1 day | Operations Champion | Exam room, Check out | Jan 22 |  |

DO: Make note of what you did and how it went. Note any problems or surprises.

Example: - The team implemented the plan for one day. 9 patients received a dose of HPV vaccine during the test day, and 7 of them needed follow up doses. - 6 of the 7 patients were given the HPV Vaccine Return Visits form. The nurse forgot to give the form to one patient. - Check Out staff scheduled 5 appointments. One patient said they would rather wait to schedule and would call in to make the appointment. - Check Out staff thought the form was helpful to guide them on when to schedule the next appointment.

- [Write in your practice’s observations here]

STUDY: Review the data and discuss observations, challenges, unexpected results, and lessons learned.

Example: - The Operations Champion used the VHealth dashboard to look at HPV vaccines given during the visits for the 1-day test period. - Process measure: All providers documented recommending the HPV vaccine to the 11 patients who were due (100%). - Primary outcome: 9 of the 11 patients agreed to get the HPV dose due (81%). Comparing to the baseline run chart, the percentage was 66% for all providers combined during the same week in 2017. - We were happy that the 5 patients (out of the 7) who needed to schedule follow up HPV doses, did so at the time of their visit. But the Nurses and MAs were concerned they might forget about it in the future.

- [Write in your practice’s results and lessons learned here]

- Process measure:

- Primary outcome:

ACT: Plan for next cycle or adopt the final plan

If this test did not work out well: ABANDON - Modify the plan based on what you learned to test a NEW strategy on a small scale in the next PDSA cycle.

If this test was successful: ADAPT - For the next PDSA cycle, either increase the SCALE (e.g., add more providers, patients, or days) or increase the SCOPE (e.g., add more tasks or steps to the workflow).

After several cycles: ADOPT - Once you have fully implemented a change that is working well and your team is satisfied with the impact, adopt it as standard practice.

Example: - The team decided to adapt the plan by moving where the form is stored to make it more visible and help remind the Nurse/MA to use it, then test again for 1 day. - In a future PDSA cycle, the team will “scale up” to test the change for 5 days.

- [Write in what you will test in the next cycle]