| PDSA CYCLE # |  | Practice Name: |  |
| --- | --- | --- | --- |

Change Option G: Offer Adolescent Vaccines During Non-Well Visits

OVERALL AIM:

By June 30, 2018, increase delivery of HPV vaccine by 10 percentage points above baseline for patients ages 11-17 seen for any office visit.

CHANGE IDEA: Establish standing orders for nurses to provide all doses of adolescent vaccines.

MEASURES (Run charts will be provided by VHealth):

1.       Primary Outcome: HPV vaccine delivery (receipt of next dose due) during all visits (% of visits)

2.       Process Measure: Missed opportunities: non-well clinic visits with patients not up-to-date for HPV vaccines (% of visits)

INSTRUCTIONS: This PDSA form contains sample text as a guide. Please modify the Plan table as needed for your practice. Next, refer to the examples in the Do, Study, and Act sections. Then fill in these sections for your practice as you carry out the PDSA cycle.

PLAN: Outline tasks and assignments for this test of change. Revise for each new PDSA cycle.

Start on a small scale or with a few steps of the entire process, then expand the scale and scope in subsequent cycles.

| Tasks | Person(s) Responsible | Where to be done | Start date (update each cycle) | Resources |
| --- | --- | --- | --- | --- |
| Champions and providers discuss and sign commitment to policy to routinely provide adolescent vaccines during non-well visits. | Physician Champion | Meeting room | Jan 10 | Provider Consensus Form |
| Champions and providers discuss and agree on protocol and workflow changes; assign Project Lead (Nurse Manager). | Physician Champion | Meeting room | Jan 17 | Sample workflow Guide to Contraindications Conditions Incorrectly Perceived as Contraindications (ACIP) |
| Operations Champion designates place in EHR to upload scanned Screening Checklist for Contraindications and posts sample checklist in staff room. | Operations Champion | EHR | Jan 19 | Screening Checklist for Contraindications - Teens |
| Nurse Manager meets with all Nurses/MAs to go over changes to workflow for non-well visits: screen for contraindications during intake, scan form into EHR, and make clinical note for provider. | Nurse Manager | Meeting room | Jan 22 | Sample workflow Vaccines When Your Child is Sick (parent flyer) |
| All Nurses and MAs implement new workflow for 1 day | Nurse Manager | Intake | Jan 23 |  |

DO: Make note of what you did and how it went. Note any problems or surprises.

Example: - The team implemented the plan for one day. - The Nurse Manager used VHealth dashboard for appointment prep, in the morning of Jan 23rd. Out of 15 appointments, 6 patients were due HPV; 3 of these were sick visit appointments. There were also 4 sick visit walk-ins who were due for an HPV vaccine dose. - Nurses and MAs screened all 10 patients for contraindications. Of the 10 patients screened, none had contraindications; - During the test day, Three MAs and 1 Nurse were asked if it was safe to get vaccines with mild illness. They responded that it was safe.

- [Write in your practice’s observations here]

STUDY: Review the data and discuss observations, challenges, unexpected results, and lessons learned.

Example: - The next day, the Operations Champion used the VHealth dashboard to look back at the patients due for HPV vaccine given during the 1-day test period. - Process measure: Of the 7 non-well visit patients due for HPV, 4 did NOT get the HPV vaccine (57%). These 4 refused the HPV vaccine, despite the provider’s recommendation, saying their child was too sick. - Primary outcome: 6 of the10 patients due for a dose of HPV vaccine received it during the visit (60%). Comparing to the baseline run chart, the percentage was 40% for all providers combined during the same week in 2017. - We thought we might lower the refusal rate if we used the “Talking Points for Staff” and the patient education flyer for the next PDSA cycle.

- [Write in your practice’s results and lessons learned here]

- Process measure:

- Primary outcome:

ACT: Plan for next cycle or adopt the final plan

If this test did not work out well: ABANDON - Modify the plan based on what you learned to test a NEW strategy on a small scale in the next PDSA cycle.

If this test was successful: ADAPT - For the next PDSA cycle, either increase the SCALE (e.g., add more providers, patients, or days) or increase the SCOPE (e.g., add more tasks or steps to the workflow).

After several cycles: ADOPT - Once you have fully implemented a change that is working well and your team is satisfied with the impact, adopt it as standard practice.

Example: - The team decided to adapt the plan by adding a step to train Nurses/Mas and staff on the “Talking Points for Staff” document, and to give the “Vaccines When Your Child is Sick” flyer to parents when child is screened as having no contraindications during a sick visit, then test in the 2nd PDSA cycle for 1 day . - Future PDSA cycles will “scale up” by testing the change for 5 days, making adjustments as needed, then testing the change for 1 month.

- [Write in what you will test in the next cycle] ]